## Plan and Details
Project Plan and Details
Below is the project plan and details, We do have attached the excel file to get better view though.
List of Topics | ID | Sub Topic | Assigned Name | Dependency(ID) | Start Date | End Date | Week | [10 empty] | Status | Comments
[7 empty] | 19 Sept - 25 Sept | 26 Sept - 2 Oct | 3 Oct - 9 Oct | 10 Oct - 16 Oct | 17 Oct - 23 Oct | 24 Oct - 30 Oct | 31 Oct - 6 Nov | 7 Nov - 13 Nov | 14 Nov - 20 Nov | 21 Nov - 27 Nov | 28 Nov - 4 Dec
Project Envisioning Stage | 1 | Form Groups | All | - | 2022-09-19 | 2022-09-20 | [11 empty] | Completed
| 2 | Research on the topic | All | 1 | 2022-09-20 | 2022-09-25 | [11 empty] | Completed
| 3 | Draft and Submit project Group & Topic on blackboard | Shrey | 2 | 2022-09-20 | 2022-09-25 | [11 empty] | Completed
Project Proposal | 4 | Draft and Submit the project Proposal & Outline | Sohaib | 3 | 2022-10-10 | 2022-10-16 | [11 empty] | Completed
Data Gathering | 5 | Finding dataset for the research questions (if anything is missing) | Raqeeb | 4 | 2022-10-10 | 2022-10-16 | [11 empty] | Completed | dataset1&2
| 6 | Draft and Submit the Project Plan & Detail | Chris | 5 | 2022-10-16 | 2022-11-05 | [11 empty] | Completed
Data Preparation | 7 | Loading datasets into dataframes | Chris | 5 | 2022-11-07 | 2022-11-07 | [11 empty] | Completed
| 8 | Checking all columns for data values and types | Chris | 7 | 2022-11-07 | 2022-11-07 | [11 empty] | Completed
| 9 | Check for missing and extreme values | Sohaib | 8 | 2022-11-07 | 2022-11-07 | [11 empty] | Incomplete
| 10 | Review for Data Preparation Steps | Raqeeb | 7 - 9 | 2022-11-07 | 2022-11-25 | [11 empty] | Incomplete
Data Cleaning | 11 | Remove Outliers | Shrey | 10 | 2022-11-08 | 2022-11-08 | [11 empty] | Incomplete
| 12 | Check for categorized columns, missing values and take action | Shrey | 11 | 2022-11-08 | 2022-11-08 | [11 empty] | Incomplete
| 13 | Column correlations | Sohaib | 12 | 2022-11-08 | 2022-11-08 | [11 empty] | Incomplete
| 14 | Review of Data Cleaning Steps | Chris | 10 - 13 | 2022-11-08 | 2022-11-25 | [11 empty] | Incomplete
Data Analysis and Visualization | 15 | Residual Plots , Correlation Plots | Raqeeb | 14 | 2022-11-09 | 2022-11-20 | [11 empty] | Incomplete
| 16 | Determine column relevancy | Sohaib | 15 | 2022-11-09 | 2022-11-09 | [11 empty] | Incomplete
| 17 | Feature Selection / Dimensionaliy Reductions | Chris | 16 | 2022-11-09 | 2022-11-20 | [11 empty] | Incomplete
| 18 | Clustering | Chris | 15 - 18 | 2022-11-09 | 2022-11-20 | [11 empty] | Incomplete
| 19 | Review Data Analysis and Visualization | Shrey | 18 | 2022-11-09 | 2022-11-25 | [11 empty] | Incomplete
Data Modeling | 20 | Train test split | Sohaib | 19 | 2022-11-10 | 2022-11-10 | [11 empty] | Incomplete
| 21 | Using models in R libraries (Caret, etc.) | Raqeeb | 20 | 2022-11-10 | 2022-11-20 | [11 empty] | Incomplete
| 22 | Determine best metrics for different research questions | Shrey | 21 | 2022-11-10 | 2022-11-20 | [11 empty] | Incomplete
| 23 | Regularization methods | Sohaib | 22 | 2022-11-10 | 2022-11-10 | [11 empty] | Incomplete
| 24 | Review All the Data Modelling Steps | Sohaib | 19 - 23 | 2022-11-10 | 2022-11-25 | [11 empty] | Incomplete
Model Selection | 25 | Compare each model | Raqeeb | 24 | 2022-11-11 | 2022-11-20 | [11 empty] | Incomplete
| 26 | Hyperparameter tuning | Shrey | 25 | 2022-11-11 | 2022-11-20 | [11 empty] | Incomplete
| 27 | Cross Validation & Bootstrapping | Chris | 26 | 2022-11-11 | 2022-11-20 | [11 empty] | Incomplete
| 28 | Performance Metrics we used and it's Interpretation, Answers each Research Questions | Chris | 27 | 2022-11-20 | 2022-11-27 | [11 empty] | Incomplete
| 29 | Review | Chris | 25 - 28 | 2022-11-20 | 2022-11-29 | [11 empty] | Incomplete
Project Report/Presentation | 30 | Write Project Report | All | 2 - 29 | 2022-11-21 | 2022-12-01 | [11 empty] | Incomplete
| 31 | Prepare Project Presentation | All | 30 | 2022-11-21 | 2022-12-02 | [11 empty] | Incomplete
| 32 | Review Project Report and Presentation | Shrey | 31 | 2022-12-01 | 2022-12-02 | [11 empty] | Incomplete
Deliverables | 33 | Review and Send Project Report, Project File , Data , Presentation | All | 30 - 32 | 2022-12-03 | 2022-12-04 | [11 empty] | Incomplete